## 0. Dashboard
SAT — Feature Planning & Review
Site Analysis Tool — Integration Tracker ¦ Generated: 2026-05-25 ¦ Target Release: 2026-06-01
STATUS SNAPSHOT
Total User Stories 20 | Stories Done (Jira) 4 | Stories In Progress 4
Stories Not Started 12 | Features with Code 9 | Open Issues 18
Contracts Written 4 / 6 needed | Sprint 3 Ready 3 services
LEGEND
Done — Jira resolved + code found
In Progress — partial / POC / unverified
Not Started — no code, no ticket
SHEETS
1. Feature Registry | All 20 stories — status, owner, code location, contract, flag, FVD
2. Integration Plan | Ordered integration queue — 13 items, prerequisites, sprint, blockers
3. Open Issues | 18 open issues — severity, owner, status
4. Build Evidence | 9 features — commit hashes, repos, key files, functions
5. Discussion Log | Team Q&A — decisions, owners, due dates
6. Sprint Plan | Sprint 0–7 — scope, velocity, status, notes

## 1. Feature Registry
Epic | Story ID | Feature / Story | Jira | Jira Status | Code Status | Owner | Points | Priority | Source Repo | Commit | SAT Service Dir | Contract | Feature Flag | FVD | Notes / Blockers
E1 | US-01 | Wind Analysis & Ventilation | SAT-4 | Done | Done — V3 in org repo (Temperature /weather/analyze-wind) + windApi.ts + WindResultsPanel | Vishwas | 13 | Must Have | SiteAnalysisToolV3/backend/Temperature/ + frontend/src/services/ | 55cd75e | services/wind/ | contracts/wind.yaml | feature.wind.climatology | FVD-09 / FVD-17 | V3 production backend supersedes POC. Open-Meteo ERA5 daily.
E1 | US-01b | Cyclone / Special Wind Events | SAT-8 | In Progress | No code | Vishwas | 8 | Must Have | — | — | services/wind/ (extend) | TBD | feature.wind.cyclone | — | No Jira ticket. No code. Needs IMD cyclone track or IBTrACS dataset.
E1 | US-02 | Temperature & Thermal Profile | SAT-9 | Done | Done — V3 in org repo (backend/Temperature/, port 8000) | Vishwas | 8 | Must Have | SiteAnalysisToolV3/backend/Temperature/ | 4bf53de | services/temperature/ | contracts/temperature.yaml | feature.temperature.thermal-profile | FVD-08 | V3 integrated.
E1 | US-03 | Rainfall & Water Management | SAT-11 | In Progress | Unverified — Karthik claims Done | Karthik | 5 | Must Have | Unknown | — | services/ (new: rainfall) | TBD | feature.rainfall.analysis | — | Backend claimed Done in spreadsheet but code not located. Must find before integration.
E1 | US-04 | Solar / Sun Path | SAT-21 | Done (spike) | Done — V3 in org repo (backend/SunPath/, port 8001, shadow engine enhanced) | Karthik | 13 | Must Have | SiteAnalysisToolV3/backend/SunPath/ | 4bf53de | services/sunpath/ | contracts/sunpath.yaml | feature.sunpath.diagram | FVD-06 | V3: shadow engine, face-shadow engine, OSM extractor added.
E1 | US-05 | Contour Maps & Slope Orientation | SAT-66 / SAT-207 | Backlog / To Do | Done — V3 in org repo (SiteAnalysisToolV3/backend/Terrain/) | — | 8 | Must Have | Site-Analysis/SiteAnalysisToolV3 — backend/Terrain/ | 4bf53de | services/geo/ (extend) | TBD | feature.geo.slope | — | SAT-66 (Backlog) and SAT-207 (To Do) — duplicate stories. Implemented in V3 Terrain backend. See FVD-10.
E1 | US-06 | Visual & Physical Site Characteristics | — | No ticket | No code | — | 13 | Must Have | — | — | TBD | TBD | feature.geo.visual | — | Needs design. Possible: Street View API, Mapbox GL, or satellite imagery.
E1 | US-07 | Flood Risk / Floodplain Mapping | SAT-18 (related) | Done (spike) | Done — V3 in org repo (backend/FloodPlains/, port 8002) | Tanmay | 5 | Should Have | SiteAnalysisToolV3/backend/FloodPlains/ | 4bf53de | services/flood/ | contracts/flood.yaml | feature.flood.risk-analysis | FVD-04 | V3 integrated. GEE chart + PDF + map renderer added.
E1 | — | GEE Interactive Map (platform) | SAT-18 (related) | Done (spike) | Done — GEE org repo | — | — | Must Have | Site-Analysis/SiteAnalysis_GEE | 0815bc7 | services/geo/ | TBD | feature.geo.map | FVD-01 | Core GEE platform. Feeds into geo service.
E1 | — | Vegetation Analysis (NDVI/EVI/SAVI) | SAT-18 | Done (spike) | Done — GEE org repo | — | — | Must Have | Site-Analysis/SiteAnalysis_GEE | 13afab7 | services/geo/ | TBD | feature.geo.vegetation | FVD-02 | NDVI + EVI + SAVI + MODIS time-series. Part of geo service.
E1 | — | Administrative Boundaries | — | No ticket | Done — GEE org repo | — | — | Must Have | Site-Analysis/SiteAnalysis_GEE | 13afab7 | services/geo/ | TBD | feature.geo.admin | FVD-03 | FAO GAUL 3-tier hierarchy. Part of geo service.
E1 | — | PDF Report Generation | SAT-23 (related) | Done (spike) | Done — GEE org repo | — | — | Should Have | Site-Analysis/SiteAnalysis_GEE | edd4c29 | services/ (report) | TBD | feature.report.pdf | FVD-05 | ReportLab PDF. Needs to pull data from all other services.
E1 | — | Next.js Frontend Platform | SAT-23 (related) | Done (spike) | Done — SiteAnalysisV2 org repo | — | — | Must Have | Site-Analysis/SiteAnalysisV2 | 0ba0e17 | apps/web/ | N/A (frontend) | — | FVD-07 | Next.js 15 + Firebase + GEE/OSM/KGIS/Bhuvan. apps/web/ bootstrapped.
E2 | US-08 | Zoning Classification | — | No ticket | No code | — |  | Must Have | — | — | TBD | TBD | feature.regulatory.zoning | — | No planning done. Possible source: Bhuvan LULC / local municipal APIs.
E2 | — | Land Use Compliance | — | No ticket | No code | — |  | Must Have | — | — | TBD | TBD | feature.regulatory.land-use | — | Dependent on US-08 zoning data.
E2 | US-09 | Accessibility Standards | — | No ticket | No code | — |  | Must Have | — | — | TBD | TBD | feature.regulatory.accessibility | — | UDCPR / NBC compliance rules. Likely rule-based engine, no external data source.
E2 | US-10 | Environmental Clearance (ECBC/IGBC/GRIHA) | — | No ticket | Done — V3 in org repo (SiteAnalysisToolV3/frontend/src/lib/energy-carbon.ts) | — |  | Must Have | Site-Analysis/SiteAnalysisToolV3 — frontend/src/lib/ | 4bf53de | TBD | TBD | feature.regulatory.env-clearance | — | Green building compliance checklist. Needs regulatory data source.
E2 | US-11 | CRZ / Eco-Zone Verification | — | No ticket | No code | — |  | Must Have | — | — | TBD | TBD | feature.regulatory.crz | — | SAT-22 spike done but no implementation. CRZ boundary data from MoEFCC.
E2 | US-12 | Viewpoints & Landmarks | — | No ticket | No code | — |  | Must Have | — | — | TBD | TBD | feature.geo.viewpoints | — | 3D visual cones needed. OSM landmark data available.
E3 | US-13 | Historical Land-Use | — | No ticket | No code | — |  | Should Have | — | — | TBD | TBD | feature.history.land-use | — | Historical satellite or cadastral data. Google Earth Engine time-series possible.
E3 | US-14 | Contamination & Heritage | — | No ticket | No code | — |  | Must Have | — | — | TBD | TBD | feature.history.heritage | — | Heritage listings from ASI / state heritage boards. Contamination: no clear data source.
E3 | US-15 | Population Density | — | No ticket | No code | — |  | Must Have | — | — | TBD | TBD | feature.socio.population | — | WorldPop or Census India 2011 raster data. GEE can serve this.
E3 | US-16 | Cultural & Religious Hubs | — | No ticket | No code | — |  | Must Have | — | — | TBD | TBD | feature.socio.cultural | — | OSM amenity tags (place_of_worship, community_centre, park). Available now.
E3 | US-17 | Schools & Hospitals Proximity | — | No ticket | No code | — |  | Must Have | — | — | TBD | TBD | feature.socio.services | — | OSM amenity=school/hospital + isochrone. OSMnx already used in Django backends.
E3 | US-18 | Local Materials | — | No ticket | No code | — |  | Should Have | — | — | TBD | TBD | feature.socio.materials | — | No external data source identified. Likely curated static dataset by region.
E1 | US-05 | Terrain Analysis (Slope/Aspect/Buildable Zones) | SAT-66 / SAT-207 | Backlog / To Do | Done — V3 in org repo (SiteAnalysisToolV3/backend/Terrain/) | V3 team | 8 | Must Have | Site-Analysis/SiteAnalysisToolV3 — backend/Terrain/ | 4bf53de | services/terrain/ | TBD | feature.terrain.analysis | FVD-10 | New Terrain backend port 8003. Slope/aspect/buildable/hazard/suitability. SAT-66 (Backlog) + SAT-207 (To Do) are duplicate stories — need resolution.
E1 | US-NEW-01 | 3D Simulation Engine (Three.js + OSM context) | SAT-218 | To Do | Done — V3 in org repo (SiteAnalysisToolV3/frontend/src/simulation/) | V3 team | 21 | Must Have | Site-Analysis/SiteAnalysisToolV3 — frontend/src/simulation/ | dc4288a | apps/web/simulation/ | N/A (frontend) | feature.simulation.3d | FVD-11 | SceneCanvas 5317 lines. Three.js + R3F. Terrain DEM, OSM context, proposal buildings, sketch detail. SAT-219/220/221 subtasks all To Do — FVD-11 docs cover them.
E2 | US-09 | NBC 2016 Constraints + Generative Design Engine | — | No ticket | Done — V3 in org repo (SiteAnalysisToolV3/frontend/src/lib/) | V3 team | 13 | Must Have | Site-Analysis/SiteAnalysisToolV3 — frontend/src/lib/ | 4bf53de | apps/web/lib/ | N/A (frontend) | feature.regulatory.nbc | FVD-12 | FAR/setbacks/coverage/parking from NBC 2016. 6 typology presets. AI enhancer scoring. NBC data accuracy unverified.
E2 | US-10 | Energy Use & Embodied Carbon (ECBC 2017) | — | No ticket | Done — V3 in org repo (SiteAnalysisToolV3/frontend/src/lib/energy-carbon.ts) | V3 team | 8 | Must Have | Site-Analysis/SiteAnalysisToolV3 — frontend/src/lib/ | 4bf53de | apps/web/lib/ | N/A (frontend) | feature.regulatory.ecbc | FVD-13 | ECBC 2017 baseline EUI × 5 climate zones. Live carbon in simulation. Embodied carbon LCA deferred.
E1 | US-NEW-02 | Pedestrian Wind + Noise + Thermal Comfort (Client-Side) | — | No ticket | Done — V3 in org repo (SiteAnalysisToolV3/frontend/src/lib/) | V3 team | 13 | Should Have | Site-Analysis/SiteAnalysisToolV3 — frontend/src/lib/ | 4bf53de | apps/web/lib/ | N/A (frontend) | feature.simulation.microclimate | FVD-14 | wind-sim.ts (CFD approx, Lawson criteria), noise-sim.ts (CPCB), thermal-comfort.ts (ISO 7730 PMV). No UI panels yet.
E1 | US-NEW-03 | BIM/CAD Exports (PDF + IFC + GLTF) | — | No ticket | Done — V3 in org repo (SiteAnalysisToolV3/frontend/src/lib/) | V3 team | 8 | Should Have | Site-Analysis/SiteAnalysisToolV3 — frontend/src/lib/ | 4bf53de | apps/web/lib/ | N/A (frontend) | feature.export.bim | FVD-15 | jsPDF A4 report, web-ifc IFC2x3, Three.js GLTFExporter GLB. IFC coordinates are x=0,z=0 placeholders. No export UI found in V3 frontend.
E1 | US-NEW-04 | Realtime Collaboration & Project Sharing | — | No ticket | Service done — in org repo (SiteAnalysisToolV3/frontend/src/services/) | V3 team | 13 | Should Have | Site-Analysis/SiteAnalysisToolV3 — frontend/src/services/ | 4bf53de | apps/web/services/ | N/A (frontend) | feature.collaboration.realtime | FVD-16 | Supabase realtime presence + invites + share tokens. Services built but SimulationRoot has no save/share UI yet. isReadOnly flag not enforced in SceneCanvas.

## 2. Integration Plan
# | Feature | Target Service | Contract | Feature Flag | Source Repo / Path | Target Path | Prerequisites | Owner | Sprint | Status | Blocker / Next Action
1 | Temperature & Thermal Profile | services/temperature/ | contracts/temperature.yaml | feature.temperature.thermal-profile | Site-Analysis-Tool/src/Backend/Temperature/ | services/temperature/app/ | None | Vishwas | Sprint 3 | Ready | None
2 | Solar / Sun Path | services/sunpath/ | contracts/sunpath.yaml | feature.sunpath.diagram | Site-Analysis-Tool/src/Backend/SunPath/ | services/sunpath/app/ | None | Karthik | Sprint 3 | Ready | None
3 | Flood Risk | services/flood/ | contracts/flood.yaml | feature.flood.risk-analysis | Site-Analysis-Tool/src/Backend/FloodPlains/ | services/flood/app/ | None | Tanmay | Sprint 3 | Ready | None
4 | Wind Analysis | services/wind/ | contracts/wind.yaml | feature.wind.climatology | Vishwas721/sat (sat04/) | services/wind/app/ | None | Vishwas | Sprint 3 | Blocked | POC in personal repo — must push to org first
5 | Geo / GEE Platform | services/geo/ | contracts/geo.yaml (TBD) | feature.geo.map | Site-Analysis/SiteAnalysis_GEE | services/geo/app/ | Temperature, Flood done | TBD | Sprint 4 | Needs contract | Write contracts/geo.yaml first
6 | Vegetation (NDVI/EVI/SAVI) | services/geo/ (extend) | contracts/geo.yaml | feature.geo.vegetation | Site-Analysis/SiteAnalysis_GEE | services/geo/app/gee_utils.py | Geo platform done | TBD | Sprint 4 | Blocked by #5 | Depends on geo service
7 | Admin Boundaries | services/geo/ (extend) | contracts/geo.yaml | feature.geo.admin | Site-Analysis/SiteAnalysis_GEE | services/geo/app/gee_utils.py | Geo platform done | TBD | Sprint 4 | Blocked by #5 | Depends on geo service
8 | Rainfall Analysis | services/ (new) | contracts/rainfall.yaml (TBD) | feature.rainfall.analysis | Unknown — locate Karthik's code | services/rainfall/ | Temperature done | Karthik | Sprint 4 | Blocked | Code not found — locate before planning
9 | Contour / Slope | services/geo/ (extend) | contracts/geo.yaml | feature.geo.slope | New — extend MERIT DEM from flood service | services/geo/app/ | Geo + Flood done | TBD | Sprint 5 | Not started | Extend existing MERIT DEM integration
10 | PDF Reports | services/ (report) | contracts/report.yaml (TBD) | feature.report.pdf | Site-Analysis/SiteAnalysis_GEE | services/report/ | All data services done | TBD | Sprint 5 | Not started | Depends on all upstream services
11 | Frontend — Map & Analysis UI | apps/web/ | N/A | All feature flags | Site-Analysis/SiteAnalysisV2 | apps/web/ | At least 1 service done | Vishwas / Dhanush | Sprint 3+ | In progress | apps/web bootstrapped. Wire service clients.
12 | Zoning / Regulatory (E2) | services/ (new) | TBD | feature.regulatory.* | None | services/regulatory/ | None | TBD | Sprint 6+ | Not started | No planning. Create Jira epic first.
13 | Socio-Cultural (E3) | services/ (new) | TBD | feature.socio.* | None | services/socio/ | None | TBD | Sprint 7+ | Not started | No planning. Create Jira epic first.

## 3. Open Issues
Feature | Issue Type | Description | Severity | Owner | Status | Resolution / Notes
Wind Analysis (US-01) | Code Location | POC at Vishwas721/sat (personal repo). Not in Site-Analysis org. Cannot be PR'd until pushed to org. | Critical | Vishwas | Resolved | V3 full implementation in Site-Analysis/SiteAnalysisToolV3 (commit 685547b). FVD-17 documents V3 wind analysis. FVD-09 POC deprecated.
Rainfall Analysis (US-03) | Code Missing | Karthik's backend marked Done in product spreadsheet but code not found in any repo. Must locate before Sprint 4. | Critical | Karthik | Open
Cyclone Events (US-01b) | No Jira Ticket | Feature in product backlog (8 pts, Must Have) with no Jira ticket, no code, no data source identified. | High | Vishwas | Partially Resolved | SAT-8 exists (In Progress). Still no code found in V3. Needs implementation.
All E2 Stories (US-08 to US-12) | No Planning | 5 Must Have stories with no Jira tickets, no owners, no code, no data sources identified. Target release June 1. | Critical | Chirag | Open
All E3 Stories (US-13 to US-18) | No Planning | 6 stories (4 Must Have) with no Jira tickets, no owners, no code. Target release June 1. | High | Chirag | Open
Sprint Planning | Process Gap | Sprint sheet ends at Sprint 2 (Dec 2025). No Sprint 3+ planning documented. 5 months of work untracked. | High | Chirag | Open
Spreadsheet Status Mismatch | Data Inconsistency | US-01 (Wind) and US-02 (Temperature) show 'In Progress' in product spreadsheet but are Done in Jira (SAT-4, SAT-9). | Medium | Chirag | Resolved | Feature Registry updated: US-01 (Wind) = Done, US-02 (Temperature) = Done. V3 in org repo confirmed.
CODEOWNERS | Repo Config | @Site-Analysis/maintainers team in CODEOWNERS not configured. PRs have no enforced reviewers. | Medium | Chirag | Open
Branch Protection | Repo Config | No branch protection rules on main. Anyone can push directly, bypassing CI and PR template. | High | Chirag | Open
Sun Path — Shadow Casting | Incomplete Feature | US-04 AC: 'Seasonal shadow patterns visualized' — not implemented in current backend. | Medium | Karthik | Open
Sun Path — Solstice Export | Incomplete Feature | US-04 AC: 'Solstice data exported for design reference' — JSON available but no dedicated export format. | Low | Karthik | Open
Flood Risk — Historical Data | Incomplete Feature | US-07 AC: 'Historical flood data integrated' — current model uses hydrology proxy, not actual event data. | Medium | Tanmay | Open
Geo Service Contract | Missing Contract | contracts/geo.yaml not written. Geo service (GEE, OSM, Bhuvan, vegetation, admin) has no OpenAPI spec. | High | TBD | Open
Rainfall Contract | Missing Contract | contracts/rainfall.yaml not written. Cannot integrate rainfall feature without contract. | High | Karthik | Open
Wind Frontend | Missing Component | No windApi.ts in apps/web/. Equivalent of temperatureApi.ts not created. | Medium | Vishwas | Open
SAT_Backend Repo | Unclear Ownership | Site-Analysis/SAT_Backend repo exists (private, empty). Unclear if this is separate from services/ in SAT monorepo. | Medium | Chirag | Open
SAT_Feature-Agents Repo | Unclear Ownership | Site-Analysis/SAT_Feature-Agents repo exists (private, empty). AI agent work scope not defined. | Medium | Sreedhana | Open
Product Vision | Documentation | Product Overview sheet has vision = 0.01 (placeholder). No defined product vision statement. | Low | Chirag | Open
Terrain Analysis (US-05) | No Org Push | backend/Terrain/ exists only in local SiteAnalysisToolV3. Must push to Site-Analysis org before Sprint 3 integration. | Critical | V3 team | Open
3D Simulation (US-NEW-01) | Not Wired to Analysis APIs | Simulation AnalysisPanel uses local proposal metrics only — does not call SunPath/Flood/Temperature backends. Wind/solar context absent. | High | V3 team | Open | Phase 2 integration work item
3D Simulation (US-NEW-01) | Persistence Not Wired | simulationProjectService.ts + collaborationService.ts exist but SimulationRoot has no save/share UI. Projects cannot be saved from simulation flow. | High | V3 team | Open
3D Simulation (US-NEW-01) | CSG Booleans Approximated | csg-ops.ts (three-bvh-csg) exists but not wired. Union/subtract/intersect use bounding-box approximation. | Medium | V3 team | Open
NBC Engine (US-09) | Data Accuracy Unverified | FAR/setback lookup tables in modeling-math.ts not independently verified against NBC 2016 Table 15 by a licensed architect. | High | V3 team | Open | Architecture review needed before prod use
Wind/Noise/Thermal (US-NEW-02) | No UI Panels | wind-sim.ts, noise-sim.ts, thermal-comfort.ts are complete libraries but no frontend panels expose them to users. | High | V3 team | Open | UI component work needed
IFC Export (US-NEW-03) | Coordinates Are Placeholders | export-ifc.ts uses x=0, z=0 for all buildings ("In a full implementation, convert lat/lng to meters"). IFC not usable in Revit until fixed. | Critical | V3 team | Open
All V3 Features (FVD-10–17) | No Jira Tickets | 8 new features in SiteAnalysisToolV3 have no Jira tickets, no sprint assignment, no story points confirmed. | Critical | Chirag | Open | Raise stories before Sprint 4 planning
Rainfall Analysis (US-03) | Code Unverified | SAT-11 exists (In Progress). Karthik claims Done but code not located in any scanned repo. Commit 9a548ef referenced in V3 git log but files not explored yet. | High | Karthik | Open | Check SiteAnalysisToolV3 commit 9a548ef. Explore frontend/src/lib/rainfall* or similar.
BIM Export IFC (US-NEW-03) | Incomplete Feature | export-ifc.ts: createBuildingMesh() uses x=0,z=0 placeholders. Comment says "In a full implementation, convert lat/lng to meters". IFC files unusable in BIM tools until fixed. | High | V3 team | Open | Implement Haversine lat/lng→XZ offset in createBuildingMesh(). Site origin = project centroid.
Simulation Libraries (FVD-12/13/14/15) | No UI Wiring | NBC generative engine, ECBC energy calc, wind/noise/thermal comfort, and BIM exports have no UI panels in V3 SimulationRoot. Libraries complete but not accessible to users. | High | V3 team | Open | Build: SimulationToolbar with export button, NBCPanel, EnergyPanel, WindComfortPanel, NoiseMappingPanel. Wire to existing store actions.

## 4. Build Evidence
Feature | Commit | Repository | Date Merged | Jira Ticket | Key Files | Key Functions / Endpoints
GEE Interactive Map | 0815bc7 | Site-Analysis/SiteAnalysis_GEE | 2025-10-05 | SAT-18 | app/main.py, app/gee_utils.py | initialize_gee(), POST /analyze-location
Vegetation Analysis | 13afab7 | Site-Analysis/SiteAnalysis_GEE | 2025-10-09 | SAT-18 | app/gee_utils.py | calculate_ndvi(), calculate_evi(), calculate_savi(), get_modis_vegetation_timeseries()
Administrative Boundaries | 13afab7 | Site-Analysis/SiteAnalysis_GEE | 2025-10-09 | — | app/gee_utils.py | get_administrative_boundaries() — FAO GAUL L1/L2/L3
Next.js Frontend Platform | 0ba0e17 | Site-Analysis/SiteAnalysisV2 | 2025-10-14 | SAT-23 | app/main.py, app/schemas/requests.py, app/schemas/responses.py, app/services/bhuvan_service.py | POST /analyze — asyncio.gather([gee, osm, bhuvan, kgis])
Solar / Sun Path | 944c5b8 | Site-Analysis/Sprint0_User_Stories | 2025-11-09 | SAT-21 | server.py | create_polar_sun_path(), create_cartesian_sun_path(), calculate_solar_events(), get_timezone()
Flood Risk Analysis | edd4c29 | Site-Analysis/SiteAnalysis_GEE | 2025-11-25 | — | app/gee_utils.py, app/pdf_generator.py, app/chart_generator.py | calculate_flood_risk() — 4 components: MERIT DEM + hydro + JRC + MODIS LULC
PDF Report Generation | edd4c29 | Site-Analysis/SiteAnalysis_GEE | 2025-11-25 | SAT-23 | app/pdf_generator.py, app/chart_generator.py | generate_pdf_report(), POST /generate-report
Temperature & Thermal Profile | local only | Site-Analysis-Tool (local) | 2026-03-26 | SAT-9 | app/routers/weather.py, app/services/climate_analytics.py, app/services/imd_weather_service.py, app/models/climate.py | GET /weather/thermal-profile, ClimateAnalyticsService.get_annual_thermal_profile()
Wind Analysis | 55cd75e | Vishwas721/sat (sat04/) | 2026-03-19 | SAT-4 | sat_wind_poc.py, backend_poc.py, benchmark_performance.py | GET /analysis/wind/climatology, fetch_gee_wind_data(), build_rose(), get_imd_season(), get_orientation_advice()
Terrain Analysis Backend V3 | local | SiteAnalysisToolV3/backend/Terrain/ | 2026-05-26 | — | app/main.py, app/terrain_utils.py, app/models.py | POST /analyze/terrain, POST /analyze/terrain/polygon, POST /profile, POST /inspect
Wind Analysis V3 (Production) | local | SiteAnalysisToolV3/backend/Temperature/ | 2026-05-26 | SAT-4 | app/routers/weather.py, frontend/src/services/windApi.ts | GET /weather/analyze-wind → WindAnalysis{rose[16], monthly[12], seasonal[4], summary.crossVentDir}
3D Simulation Engine | local | SiteAnalysisToolV3/frontend/src/simulation/ | 2026-05-26 | — | app/SimulationRoot.tsx, components/scene/SceneCanvas.tsx (5317 lines), utils/terrain-dem.ts, lib/osm-fetch.ts | Terrain DEM (Mapbox RGB), OSM context (Overpass), Three.js scene, Sketch detail editor
NBC + Generative Engine | local | SiteAnalysisToolV3/frontend/src/lib/ | 2026-05-26 | — | lib/nbc-constraints.ts, lib/modeling-math.ts, lib/generative-engine.ts, lib/ai-enhancer.ts | calculateNBCConstraints(), generateVariants(), scoreVariant() — 5 India climate zones × 6 typologies
Energy & Carbon (ECBC 2017) | local | SiteAnalysisToolV3/frontend/src/lib/ | 2026-05-26 | — | lib/energy-carbon.ts | calculateBuildingEUI(), calculateTotalEnergyUse() — ECBC 2017 baselines × 5 climate zones
Wind/Noise/PMV Simulations | local | SiteAnalysisToolV3/frontend/src/lib/ | 2026-05-26 | — | lib/wind-sim.ts, lib/noise-sim.ts, lib/thermal-comfort.ts | calculateWindComfortGrid() (Lawson), calculateNoiseGrid() (CPCB), calculatePMV() (ISO 7730)
BIM/CAD Exports | local | SiteAnalysisToolV3/frontend/src/lib/ | 2026-05-26 | — | lib/export-pdf.ts (jsPDF), lib/export-ifc.ts (web-ifc), lib/export-gltf.ts (Three.js GLTFExporter) | generateProjectReport() → PDF Blob, exportBuildingsToIFC() → IFC2x3 Blob, exportBuildingsToGLTF() → GLB Blob
Realtime Collaboration Services | local | SiteAnalysisToolV3/frontend/src/services/ | 2026-05-26 | — | services/collaborationService.ts, services/realtimeService.ts, services/simulationProjectService.ts, hooks/useCollaborationStore.ts | inviteCollaborator(), broadcastModelChange(), saveSimulationProject() — Supabase Realtime + Presence

## 5. Discussion Log
Date | Feature / Area | Topic / Question | Decision / Outcome | Owner | Due Date | Status
2026-05-25 | Wind Analysis (US-01) | Vishwas: when will sat04/ POC be pushed to Site-Analysis org? |  | Vishwas |  | Open
2026-05-25 | Rainfall (US-03) | Karthik: where is the rainfall backend code? Claimed Done in spreadsheet. |  | Karthik |  | Open
2026-05-25 | Cyclone (US-01b) | Does this need a separate Jira ticket and sprint? Who owns data sourcing (IMD/IBTrACS)? |  | Vishwas |  | Open
2026-05-25 | E2 Regulatory | Should E2 stories be deferred past June 1 release? None have code, owners, or data sources. |  | Chirag | 2026-05-30 | Open
2026-05-25 | SAT_Backend repo | Is SAT_Backend a separate deployment or should everything live in SAT/services/? |  | Chirag |  | Open
2026-05-25 | SAT_Feature-Agents | What is the AI agents scope? Sreedhana: define what goes in this repo vs SAT/services/. |  | Sreedhana |  | Open
2026-05-25 | Branch Protection | Enable branch protection on main + require 1 reviewer before merging? |  | Chirag | 2026-05-27 | Open
2026-05-25 | Release Scope | What is the June 1 release scope? E1 only? Which E1 stories are in/out? |  | Chirag | 2026-05-27 | Open
2026-05-25 | Geo Service | Who owns geo service integration? SiteAnalysis_GEE code needs porting. |  | TBD |  | Open
2026-05-25 | PDF Reports | PDF report should aggregate all services. Define report schema before integration. |  | TBD |  | Open

## 6. Sprint Plan
Sprint | Type | Start | End | Velocity (pts) | Stories / Scope | Status | Notes
Sprint 0 | Spike | 2025-10-27 | 2025-11-10 |  | SAT-18, SAT-19, SAT-20, SAT-21, SAT-22, SAT-23 | Done | All spikes resolved. GEE, Solar, Vegetation, Flood, PDF, Admin Boundaries explored.
Sprint 1 | Sprint | 2025-11-14 | 2025-11-28 | 60 | US-01 to US-07 | Partial | US-04 (solar), US-07 (flood) resolved. US-01, US-02 slipped.
Sprint 2 | Sprint | 2025-12-03 | 2025-12-17 | 47 | SAT-04, SAT-08, SAT-11, SAT-66, US-06 | Partial | SAT-4 (wind) + SAT-9 (temperature) resolved March 2026 — 3 months late.
Sprint 3 (planned) | Sprint | 2026-06-02 | 2026-06-16 | 40 | Integrate: Temperature, SunPath, Flood into SAT monorepo. Wind after repo push. | Not started | First integration sprint. All 3 backends ready. Set up CI smoke tests.
Sprint 4 (planned) | Sprint | 2026-06-17 | 2026-06-30 | 40 | Integrate: Wind, Geo platform, Vegetation, Admin Boundaries. Find Rainfall code. | Not started | Geo contract must be written first. Rainfall blocker must be resolved.
Sprint 5 (planned) | Sprint | 2026-07-01 | 2026-07-14 | 35 | PDF Reports, Contour/Slope, Cyclone (if ticket created), Frontend wiring. | Not started | Aggregation sprint. PDF depends on all data services being up.
Sprint 6+ (TBD) | Sprint | TBD | TBD |  | E2 Regulatory stories (US-08 to US-12) — if scope confirmed. | Not started | No planning done. Create Jira epic and assign owners first.
Sprint 7+ (TBD) | Sprint | TBD | TBD |  | E3 Socio-Cultural stories (US-13 to US-18). | Not started | No planning done. Create Jira epic and assign owners first.
Sprint 4 (planned) | Sprint | 2026-06-30 | 2026-07-14 | 55 | Push V3 backends to org (Terrain, Temperature/Wind, SunPath V3, FloodPlains V3). Wire simulation to analysis APIs. Add export UI. Raise Jira stories for FVD-10 to FVD-17. | Not started | V3 validation complete 2026-05-26. 8 new FVDs written (FVD-10–17). Primary gaps: no org push, no Jira tickets, simulation not wired to APIs.